## This Phase
< Name Venture >
Critical Path | 2011: PreSeed | [11 empty] | 2012: Seed | [5 empty] | Remarks
Business plan (review) | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June
and move to Seed
Marketing: | bar: 2011: PreSeed Mar to 2011: PreSeed Aug
xx
Go-to-Market Partners: | bar: 2011: PreSeed Aug to 2012: Seed Apr
Technical: | bar: 2011: PreSeed Jan to 2012: Seed June
xx
xx
Supply chain: | bar: 2011: PreSeed Mar to 2012: Seed May
Clinical/Regulatory: | bar: 2011: PreSeed Aug to 2012: Seed June
Ecosystem: | bar: 2011: PreSeed June to 2012: Seed June
Team: | bar: 2011: PreSeed July to 2011: PreSeed Aug; 2011: PreSeed Oct to 2012: Seed Jan
| 2011: PreSeed | [11 empty] | 2012: Seed
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June

## Overview Plan
< Name Venture >
| 2011 |  |  |  | 2012 |  |  | 2013 |  |  |  | 2014 |  |  | 2015 |  | 2016 |  |  | 2017 |  |  | 2018
| H1 |  | H2 |  | H1 | H2 |  | H1 |  | H2 |  | H1 | H2 |  | H1 | H2 | H1 |  | H2 | H1 |  | H2
Milestones EV: | x |  |  | x |  | x |  |  |  | x |  |  | x |  |  | x |  |  |  |  | x
Tasks: | x |  |  |  | x |  |  |  | x | [5 empty] | x |  |  |  | x
[6 empty] | x |  |  |  | x |  |  |  | x |  |  |  | x
| x |  |  |  | x | [7 empty] | x
[10 empty] | x | [5 empty] | x
Team: | x | x | x | x | [5 empty] | x |  |  | x
Bell Mason: | PreSeed |  |  |  | Seed |  | Alpha |  |  |  | Beta |  |  |  |  | Market calibration
Note on J8: Ron Kroon: Validated VPH Lead customers engaged; using the solution in (pre-)clinical experiments.
Note on B15: Ron Kroon: Venture concept plan; plan for business plan, outlining the below + key resoucres required going forward, areas to be explored / risks to be reduced in Seed. Product/service: - Venture platform: + what's the offering, what makes it unique + essential elements which need to be created, purchased or partnered for + strategic link to Philips, synergies - business model options, product/service options, prospective customers, potential value propositions, ... (draft VPH), assumptions which will need to be tested - outline of development plan (requirements, schedules, incremental milestones) - spec for MVP to be delivered to lead customers - plan to develop MVP, development environment in place (tools, processes), development team for MVP in place Market: - Initial 1-on-1 interviews with prospective customers, other market research, plan for market segmentation efforts - Value network and control points - potential compettitors and competing technologies - CR/RA scenarios and of reimbursement landscape - Fit to Philips strategy, benefits for Philips, synergies - Plan to introduce MVP to lead customers and to capture feedback in place. Plan to support MVP. People - VM (champion), CTO in place, HR plan for next phase - Committed corporate sponsor Finance: - Funding for Seed committed, based on itemized request
Note on F15: Ron Kroon: Full bussiness plan, describing below items + venture exit strategy / landing spot + active lead customers Product/service: - Product/service spec, architecture, detailed development schedule/plan (incl dedicated release Alpha products) and required partnerships - MVP introduced to lead customers, generating feedback - Manufacturing / supply chain plan in place. Plan includes creation of Alpha product. Market: - Validated VPH - Marketing plan + Refinement & prio of segments and targets; incl plan to develop these markets + CR/RA targets and plan, reimbursement strategy defined + Positioning & launch strategy; NPI plan; plan to engage lead customers (listed by name) + Detailed value network analysis; incl control points & plan to master these control points + Compettitive landscape and SWOT + Branding strategy + First sales plan - Partners identified or in place in case crucial for launch - Plan to introduce and support Alpha product to Earlyvangelists (cross the first chasm) People - Core team in place, HR plan for next phase - Committed champion in place - Advisory board in place Finance: - Funding strategy defined (until exit), funding for next phase committed - Underpinned financial plan; scenario's + associated exit path (top-level Decision Tree Analysis)
Note on I15: Ron Kroon: Earlyvangelists using the Alpha product version. Business plan (see Seed) updated on Alpha product/process feedback. Product/service: - Alpha product built and running at lmited number of Earlyvangelist sites. - Where applicable the Alpha product is first test of the processes of development, marketing, customer support, supply chain, partnerships, and improvements should be made on the feedback. Market: - Marketing plan for beta: updated plan for Seed (strategic market intro; plan to Cross the Chasm - see Moore; full sales plan) + full NPI process People - VM is primary spokesperson and culture leader - Team in place to execute Beta activities, incl sales and service - High-octane sales person on board Finance: - Funding plan updated - Updated business scenarios incl associated exit paths
Note on M15: Ron Kroon: Launch took place according to product introduction strategy in selected market segment / selected customer group (crossed the chasm to early majority). Feedback on full working of all processes and partnerships. Product/service: - Beta test results used to plan for scaling of the business (in the tornado). Market: - System in place to track sales and service performance, and customer satisfaction People - HR plan in place aimed at retaining core team and attracting new talent in line with expected scling up of the business Finance: - Funding for scaling up is secured - Review of financial / business scenarios incl associated exit paths
Note on T15: Ron Kroon: Business scaled up, maturing. Reach cash positive. Feedback on scaling of all processes and partnerships, and adaptations made continuously based on the feedback. Product/service: - Continuous improvement based on market feedback, possible next release. Market: - Maturing the business - Plans to enter new geographies, customer/market segments etc. are in place and/or executed at the right time People: - Full exec team, incl CFO in place / stable - Organisation prepared for HR plan in place aimed at retaining core team and attracting new talent in line with expected scaling up of the business Finance: - Funding for scaling up is secured - Review of financial / business scenarios incl associated exit paths

## Risks
< Name Venture >
DATE: | 2011 07 07
Key word | Risk description | Risk Mitigation | Likelihood | Impact
|  |  | 6 | 7
|  |  | 8 | 6
|  |  | 6 | 9
|  |  | 8 | 7
|  |  | 5 | 9
|  |  | 2 | 10
|  |  | 7 | 8
|  |  | 3 | 7
|  |  | 3 | 4
|  |  | 5 | 8
Note on E6: Ron Kroon: Expected that initially EPs will like CAM -and pay the premium for CAM- for its visualisation capability; enabling them to take control of the procedure. Later they will demand outcome improvement.
Note on E8: Ron Kroon: Need to find other partner then. Medtronic is interested!
Note on D12: Ron Kroon: We did not prove yet as to wether we can detect lesion continuity. The data from the laser-balloon indicates continuity of lesion to play a major role.
Note on D13: Ron Kroon: First IP Risk assessment revealed no blockers. Complementary IP Risk assessment planned shortly. Various details of product design still open, therefore current assessments still on global level.
Note on C14: Ron Kroon: If risk really happens, then spin out but have to pay damages to BSC (only after commercial agreement signed - not taken into account at this moment hence impact 4, but rises to 8 after signing, although probability will drop then to 1-2).